## Slide 1
Project Title: Increase Pneumonia Vaccine Compliance of B6 Unit
Project Leader: Varun Putta
Project Sponsors: Dr. Hadeel Alkhairw
Team Members: this is to identify the QI team members who participated in the project
 | PDSA / ACTION PLANS | PERSON RESPONSIBLE
1 | Enhance Patient Education Materials | QM
2 | Create Visual Aids and Reminders for Staff – QR Code with PNA Vaccine Material | QM
3 | Integrate Vaccine Orders into Admission/Discharge Protocols | Medical Staff
4 | Revise Discharge Workflow | Medical Staff
Outcome Measure – % of patients that are PNA Vaccine Compliant
Process Measure – Total Pneumococcal vaccination given in B6
Equity Lens – Comparison of Vaccine Compliance: Hispanic and Black Populations vs. Total
Balancing Measure – Monitoring the % of Patients who had Length of Stay between 2-7 days(More than 2 & less than 7 days)
Long-Term Sustainability Plan
To ensure long-term sustainability of pneumonia vaccine compliance, we will integrate vaccine orders into admission and discharge protocols, streamlining the process for staff and patients. Enhancing the discharge workflow will include a checklist for vaccination status and follow-up scheduling. We will develop user-friendly patient education materials and create visual aids to remind staff of vaccine importance. Continuous monitoring through data tracking and regular review meetings will facilitate ongoing improvements, while partnerships with local health organizations will help sustain awareness and resources.
AIM
Primary Drivers
Secondary Drivers
Increase Pneumonia Vaccine Compliance of B6 Unit
Inefficient Vaccine Ordering and Administration Process
Insufficient Communication and Education
Postponement of Vaccine Orders
Lack of Patient Understanding of Vaccine Importance
Integrate Vaccine Orders into Admission/Discharge Protocols
Change Ideas
Inadequate Staff Training on Vaccine Protocols
Enhance Patient Education Materials
Revise Discharge Workflow
Create Visual Aids and Reminders for Staff
Elmhurst
AIM STATEMENT | Increase pneumonia vaccine compliance of the B6 Unit by 10% from baseline 45.57% to 55% between June 2, 2024 to Oct 31 2024
Chart: 
| May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | 2023 | 2024
Vaccine Compliant | 0.51049 | 0.60959 | 0.54268 | 0.55495 | 0.45324 | 0.56081 | 0.5748 | 0.45139 | 0.52143 | 0.45588 | 0.47333 | 0.51479 | 0.4557 | 0.53543 | 0.54615 | 0.57647 | 0.5137 | 0.58667 | 0.52113
Chart: 
| 23-May | 23-Jun | 23-Jul | 23-Aug | 23-Sep | 23-Oct | 23-Nov | 23-Dec | 24-Jan | 24-Feb | 24-Mar | 24-Apr | 24-May | 24-Jun | 24-Jul | 24-Aug | 24-Sep | 24-Oct | 24-Nov | Grand Total *
Total population vaccine compliance | 51.05 | 60.96 | 54.27 | 55.49 | 45.32 | 56.08 | 57.48 | 45.14 | 52.14 | 45.59 | 47.33 | 51.48 | 45.57 | 53.54 | 54.62 | 57.65 | 51.37 | 58.67 | 52.11 | 52.47
Hispanic Vaccine compliance | 24.48 | 33.56 | 26.83 | 28.02 | 22.3 | 30.41 | 30.71 | 23.61 | 23.57 | 23.53 | 23.33 | 25.44 | 21.52 | 29.92 | 26.15 | 29.41 | 26.03 | 26 | 30.99 | 26.61
Black Compliance | 16.6667 | 60 | 60 | 44.4444 | 11.1111 | 53.8462 | 71.4286 | 35.7143 | 81.8182 | 62.5 | 46.6667 | 58.8235 | 56.25 | 53.8462 | 60 | 45.4545 | 40 | 58.3333 | 47.3684 | 47.7
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | 2023 | 2024
Total | 3 | 2 | 9 | 5 | 7 | 6 | 2 | 5 | 6 | 5 | 4 | 1 | 4 | 4 | 7 | 5 | 3 | 6 | 10 | 4 | 7 | 5
Chart: 
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
% | 5.6208 | 5.2852 | 4.5302 | 3.8591 | 5.6208 | 4.698 | 6.4597 | 4.3624
Notes: The driver diagram is optional and is inserted here for ease of use. Feel free to insert an alternative display of your improvement plan.